## Risk Register
Risk ID | Date Identified | Risk Description | Probability (1-5) | Impact (1-5) | Mitigation Strategy | Status
RSK-001 | 2026-06-15 | Mock data generation fails to simulate realistic chronological progression of candidates across stages. | 4 | 5 | Implement sequential timestamp logic in Python using Faker, forcing Stage N+1 date > Stage N date. | Open
RSK-002 | 2026-06-15 | Google Sheets API rate limits triggered by frequent Python updates. | 3 | 4 | Batch write data into Sheets rather than row-by-row insertion using gspread batch_update. | Open
RSK-003 | 2026-06-15 | Looker Studio struggles with complex calculated fields for SLA breaches. | 2 | 3 | Compute all complex SLAs and time-deltas directly in SQL/Python before loading to Sheets. | Open

## Change Request Log
CR ID | Date Requested | Requesting Stakeholder | Proposed Modification | Impact Analysis | Approval Status
CR-001 | 2026-06-15 | Hiring Managers | Add 'University' and 'Major' fields to track quality of hires per academic institution. | Requires altering SQL Schema for Candidates table and updating Python Faker script. Low risk. | Approved
CR-002 | 2026-06-15 | Recruitment Managers | Implement a 'Reason for Drop-off' category for candidates rejected at Final Interview. | Adds 1 new column to Applications table. Requires mapping logic in BI Dashboard. | Pending Review

## KPI Scorecard
Metric Category | Specific KPI | Business Target | Actual Calculated Result | Variance / Status | Notes
Efficiency | Automated Report Prep Time | < 60 minutes | TBD (Target: 50-60 mins) | TBD | Will be measured during Phase 3 cron job execution.
Pipeline | Resume Screen to Interview Conversion | > 25% | TBD | TBD | Calculated in Looker Studio.
SLA | Resume Screen Turnaround Time | < 3 Days | TBD | TBD | Crucial for Recruiter Dashboard.
Quality | Final Offer Acceptance Rate (OAR) | > 80% | TBD | TBD | Calculated on Executive Dashboard.

## Funnel Logic
Stage Order | Funnel Stage Name | Action Definition | SLA Threshold (Days)
1 | Application Received | Candidate profile created in DB. | 0
2 | Resume Screening | Recruiter reviews criteria fit. | 3
3 | First Round Interview | HR / Behavioral screening call. | 5
4 | Technical Interview | Live coding / HM assessment. | 7
5 | Offer Extended | Final decision & contract negotiation. | 3