Scope Document

Project Title: Recruitment Operations & Hiring Funnel Analytics Platform

Document Version: Version 1.0

Project Duration: 5 Weeks

Introduction

This Scope Document defines the boundaries, objectives, deliverables, and limitations of the Recruitment Operations & Hiring Funnel Analytics Platform project.

The purpose of this document is to establish a clear understanding of what is included within the project scope and what is excluded from the project. This helps ensure that stakeholders have a common understanding of project expectations and deliverables throughout the project lifecycle.

Project Overview

The Recruitment Operations & Hiring Funnel Analytics Platform is designed to improve visibility into campus recruitment activities by providing recruitment analytics, hiring funnel insights, recruiter performance tracking, and automated reporting capabilities.

The system will collect recruitment-related data, analyze candidate progression through different hiring stages, and present actionable insights through dashboards and reports.

The project will support recruitment operations involving:

- 500+ Students

- 50+ Recruiting Companies

- 1,000+ Job Applications

Project Objectives

The primary objectives of the project are:

- Track candidate progression across recruitment stages.

- Measure hiring funnel conversion rates.

- Analyze candidate drop-off trends.

- Monitor recruiter workload and performance.

- Automate recruitment reporting processes.

- Develop executive dashboards for recruitment analytics.

- Improve stakeholder visibility into recruitment operations.

In Scope

The following features and activities are included within the scope of this project:

Data Management

- Creation of recruitment datasets.

- Storage of recruitment data in a relational database.

- Management of student, recruiter, company, application, interview, and offer data.

Recruitment Analytics

- Hiring funnel analysis.

- Candidate conversion rate analysis.

- Recruiter workload analysis.

- Offer acceptance analysis.

- Time-to-hire analysis.

- Candidate drop-off analysis.

Reporting

- Automated KPI reporting using Python.

- Weekly recruitment performance reports.

- Recruiter performance reports.

- Hiring funnel summary reports.

Dashboard Development

- Executive Recruitment Dashboard.

- Recruiter Performance Dashboard.

- Hiring Funnel Analytics Dashboard.

- Interactive visualizations using Looker Studio.

Project Management Activities

- Project planning and documentation.

- Stakeholder analysis.

- KPI definition and tracking.

- Risk management.

- Change request tracking.

- Project status reporting.

Out of Scope

The following features and activities are excluded from the scope of this project:

Recruitment Automation

- Resume parsing.

- AI-based candidate screening.

- Automated interview scheduling.

- Candidate recommendation systems.

Applicant Tracking System Features

- User login and authentication.

- Candidate profile management.

- Job posting management.

- Real-time application tracking portal.

Advanced Technologies

- Machine Learning models.

- Artificial Intelligence-based hiring recommendations.

- Predictive hiring analytics.

- Chatbot integration.

Mobile Applications

- Android application development.

- iOS application development.

External Integrations

- LinkedIn integration.

- Third-party recruitment platform integration.

- Email automation platforms.

Key Deliverables

The project will deliver the following outputs:

Documentation Deliverables

- Business Problem Statement

- Project Charter

- Stakeholder Register

- Stakeholder Analysis

- Scope Document

- KPI Definitions

- Risk Register

- Project Closure Report

Technical Deliverables

- Recruitment Database

- SQL Query Library

- Python Reporting Automation Script

- ER Diagram

Dashboard Deliverables

- Executive Dashboard

- Recruiter Performance Dashboard

- Hiring Funnel Dashboard

Testing Deliverables

- Test Cases

- Test Execution Report

- Validation Report

Constraints

The project is subject to the following constraints:

- Limited project duration of 5 weeks.

- Academic project environment.

- Simulated recruitment data.

- Limited access to real-world recruitment systems.

- Availability of required software tools.

Assumptions

The project assumes that:

- Recruitment data can be generated or simulated for analysis.

- Stakeholder requirements are clearly defined.

- SQL, Python, Google Sheets, Jira, and Looker Studio are available.

- Data quality is sufficient for analytics and reporting purposes.

- Project deliverables will be completed within the planned schedule.

Project Boundaries

The project focuses on recruitment analytics and reporting.

The project does not attempt to replace a complete Applicant Tracking System (ATS). Instead, it provides analytical insights into recruitment operations using historical and operational recruitment data.

The primary focus is on:

- Data analysis

- Reporting

- Dashboard development

- Recruitment performance monitoring

rather than recruitment process execution.

Scope Acceptance Criteria

The project scope will be considered successfully completed when:

- Recruitment database is developed.

- Recruitment data is available for analysis.

- KPI calculations are implemented.

- Three dashboards are created.

- Automated reporting scripts are developed.

- Project documentation is completed.

- Stakeholder reporting requirements are satisfied.

Conclusion

The Recruitment Operations & Hiring Funnel Analytics Platform project aims to improve recruitment visibility, reporting efficiency, and decision-making through data analytics and dashboard reporting. This scope document establishes the boundaries of the project and serves as a reference for stakeholders throughout the project lifecycle to ensure successful project delivery.