## Stakeholder Register
Stakeholder ID | Stakeholder Name | Role in Project | Interest Level | Influence Level | Key Expectations | Communication Method | Communication Frequency
ST-001 | Placement Officer | Project Sponsor | High | High | Recruitment visibility, KPI reporting, project success | Meetings, Dashboard Reports | Weekly
ST-002 | Recruiters | End Users | High | Medium | Candidate tracking, workload monitoring, recruitment reports | Email, Dashboard Reports | Weekly
ST-003 | Hiring Managers | Decision Makers | High | High | Hiring funnel performance, candidate progress visibility | Meetings, Reports | Bi-Weekly
ST-004 | Students | Candidates | Medium | Low | Fair recruitment process and placement opportunities | Email Notifications | Monthly
ST-005 | PMO Team | Reporting and Governance Team | High | Medium | Accurate reporting, project tracking, documentation | Team Meetings | Weekly
ST-006 | Project Development Team | System Development | High | Medium | Clear requirements and project completion | Team Meetings | Daily
ST-007 | University Management | Executive Stakeholders | Medium | High | Placement performance and hiring outcomes | Executive Reports | Monthly

## Stakeholder Analysis
Stakeholder Name | Interest Level | Influence Level | Stakeholder Category | Engagement Strategy
Placement Officer | High | High | Manage Closely | Regular updates and dashboard demonstrations
Recruiters | High | Medium | Keep Engaged | Gather reporting requirements and feedback
Hiring Managers | High | High | Manage Closely | Share hiring analytics and progress reports
Students | Medium | Low | Keep Informed | Communicate placement opportunities and status updates
PMO Team | High | Medium | Keep Engaged | Weekly project review meetings
Project Development Team | High | Medium | Keep Engaged | Daily task tracking and progress discussions
University Management | Medium | High | Keep Satisfied | Monthly executive summaries

## Stakeholder Communication Plan
Stakeholder | Information Shared | Communication Method | Frequency | Owner
Placement Officer | KPI Reports, Dashboard Updates | Meetings, Reports | Weekly | Project Lead
Recruiters | Recruiter Performance Metrics | Email, Dashboard | Weekly | Project Lead
Hiring Managers | Hiring Funnel Reports | Meetings | Bi-Weekly | Project Lead
Students | Recruitment Updates | Email | Monthly | Placement Cell
PMO Team | Project Progress Reports | Meetings | Weekly | Project Lead
Development Team | Development Tasks and Status | Team Meetings | Daily | Project Lead
University Management | Executive Summary Reports | Reports | Monthly | Placement Officer